## Sheet 1 - Milestone Review
Milestone Review
Milestone | Expected Completion Date | Actual Completion Date | NOTES
Approved Topic Proposal | Sept 6 | Sept 6
Design Review Meeting | 2020-10-16 | 2020-10-11
Tool Selection Review Meeting | 2020-10-16 | 2020-10-11
SPMP | 2020-10-16 | 2020-11-20 | Had to edit the doc to ensure it was up-to-date for the submission
Milestone Review | 2020-11-13 | 2020-11-20 | Waited for a little bit more of the project to be done before completing the review
System Test Plan | 2020-11-28 | 2020-11-20
Presentation | 2020-12-14 | 2020-12-07